## KPI Backlog
Ref | Component Name | KPI Ref | Sub-Component | Phase | KPI / Deliverable | Measurement Basis | Target / Threshold | Sign-Off Basis | Status | What we have today | What's still missing
1 | Foundation & Security | C1-SC1 | Cloud environment provisioning | Phase 1 | Agreed core environments established | Count of agreed environments provisioned and accessible | 100% of agreed Dev, Test and Production environments live | Environment inventory, cloud console evidence, architecture diagram | Partial | Dev VM `iox-vm-01` live in Azure UAE North (D2s_v3, public IP 20.203.125.83). Resource group iox-rg tagged app=IOX-OS. Public IP+NSG+VNet+OS disk all provisioned. | Separate Test environment not yet stood up. Architecture diagram not produced. Environment inventory not formalised.
1 | Foundation & Security | C1-SC2 | Infrastructure as Code | Phase 1 | IaC deployment baseline implemented | Percentage of core environments deployed through approved IaC scripts | 100% of core environments deployable through IaC | IaC repository, deployment logs, version-controlled templates | Partial | `scripts/azure-bootstrap.sh` (idempotent post-provision setup), committed in repo, re-runnable. NSG and VM created via documented `az` CLI commands. | No declarative IaC (Terraform/Bicep/ARM). Bash bootstrap is procedural. VM-creation steps live in chat history, not in a versioned template.
1 | Foundation & Security | C1-SC3 | Identity and access management | Phase 1 | Role-based access model configured | Ability to apply user roles and permission configurations | At least 2 distinct roles created and implemented across application services | Access control matrix, user access test record, security configuration evidence | Partial | NextAuth v5 + Drizzle adapter wired at `/api/auth/[...nextauth]`. UserRole enum: ADMIN, DEVELOPMENT_MANAGER, VIEWER + SUPER_ADMIN label. Per-module permission helpers (`canAccessProject`, `canAccessMasterplan`, etc.). Mock IOX session honours roles. | Only one seeded user (Arjun, SUPER_ADMIN). No 2nd distinct role actively in use. Access control matrix not documented. Security config evidence not exported.
1 | Foundation & Security | C1-SC4 | Data protection controls | Phase 1 | Encryption controls implemented | Percentage of in-scope environments and services with encryption enabled | 100% encryption at rest and in transit for in-scope services | Security settings export, configuration evidence, compliance checklist | Partial | Azure Premium SSD = encryption at rest by default (platform-managed key). Postgres connection on localhost (no transport needed). Anthropic API calls go over HTTPS. .env permissions 600 on VM. | Public HTTP traffic served on port 80 — no TLS. Need certbot/Let's Encrypt for HTTPS. Compliance checklist not produced.
1 | Foundation & Security | C1-SC5 | Security assurance | Phase 3 | Independent security validation completed | Number of unresolved critical vulnerabilities at milestone sign-off | 0 critical vulnerabilities outstanding | Penetration test report, remediation log, assessor confirmation | Not Started | Nothing yet. | Pen test not commissioned. Vulnerability scan not run. Remediation log doesn't exist.
2 | Data & Architecture | C2-SC1 | Target architecture definition | Phase 1 | Core architecture defined and approved | Completion of logical and physical architecture pack | Approved architecture pack issued | Architecture diagrams, architecture decision record, approval note | Partial | Inline architectural docs (CLAUDE.md, BACKEND.md, PROJECT.md, UI.md, modules/*/README implied by file tree). Schema definitions are self-documenting. ProcureX migration plan captured in chat. | No single 'architecture pack' artefact. No ADRs (Architecture Decision Records). No formal approval note.
2 | Data & Architecture | C2-SC2 | Shared data model | Phase 2 | Data model defined and deployed | Core shared data entities/models designed and implemented | Core shared data models deployed | Shared data schema being used by multiple applications | Strong | One Postgres database, two ORMs: Prisma owns 17 tables (User, Masterplan, BoqRun, Configuration, …) used by CostX + BOQs + summary screens; Drizzle owns 48 `px_*` tables used by ProcureX. Users referenced across modules. ConfigModelEntry consumed by 5+ pages. | Formal 'shared data schema' diagram. Documentation of which app uses which entity.
2 | Data & Architecture | C2-SC3 | Data access and retrieval | Phase 2 | Query and retrieval of data in shared and application data models | Key queries to be defined to showcase successful access to data models | Test queries to return expected results showing (if appropriate) test data | Test scripts, test execution report, sample output validation | Partial | Live working queries across both ORMs: getMasterplans, getBenchmarkProjects, getCostModelEntries, getCategoryStatuses, etc. Demo data seeded (28 masterplans, 22 benchmarks, 6 procurex projects, 18 tenderers, 960 cost model entries). Each route smoke-tested HTTP 200. | No formal automated test suite (Vitest/Jest). No execution report. Smoke tests are ad-hoc curl, not codified.
2 | Data & Architecture | C2-SC4 | Modular service design | Phase 2 | Services separable from other application services | Showcase that modules are deployable independently | 100% of launch modules independently deployable | Module deployment evidence, dependency map, architecture review | Weak | Logical modularity: code organised into `app/{costx,boqs,procurex,benchmarking,...}` route groups and `modules/{identity,workspace,procurex,…}` domain folders. Each module is self-contained per the faithful-port rule. | Physical modularity is monolithic — all modules deploy as one Next.js process. No independent service builds. No dependency map.
3 | Integration Capability | C3-SC1 | API and integration design | Phase 1 | Integration architecture and API specification completed | Completion of API and interface capability | API configuration documented | API specification pack, integration architecture document, approval record | Partial | API surface exists: `app/api/*`, `app/procurex/api/*`, server actions in `modules/*/actions.ts`. Routes auto-documented by Next.js file-system convention. | No OpenAPI/Swagger spec generated. No integration architecture document. No approval record.
3 | Integration Capability | C3-SC2 | API gateway implementation | Phase 2 | Secure API gateway deployed | Gateway operational status against agreed design | API gateway live with agreed security controls active | Gateway configuration evidence, deployment record, security checklist | Partial | Nginx reverse proxy live in front of Next.js on the VM. Proxies all traffic, sets large body limits (1024M for tender uploads), keeps-alive long extraction reads. | Nginx is a reverse proxy, not a full API gateway. No rate limiting, no per-endpoint auth, no centralised request logging, no quota/throttling. Should adopt Azure API Management or similar for production.
3 | Integration Capability | C3-SC3 | System-to-system connectivity | Phase 2 | Application service integration test cases executed | All integration test cases passed | 100% pass rate on defined integration tests | Integration test report, test logs, transaction evidence | Not Started | Ad-hoc smoke tests run during deploys (curl /procurex, /costx, etc.). All routes verified 200 manually. | No integration test framework wired. No test cases defined. No CI test job (CI currently only builds + deploys).
3 | Integration Capability | C3-SC4 | Bidirectional data exchange | Phase 3 | End-to-end application service data exchange proven | Number of successful bidirectional transactions completed | Minimum agreed set of test transactions completed successfully | Transaction logs, sample records, demonstration output | Partial | Anthropic API integration is fully bidirectional — request → agent loop → submit_verdict tool call → schema validation → persist. Verified end-to-end with a real FoT PDF (4 pages, 2401 in / 1244 out tokens). Workflow run output stored in px_workflow_run. | Other 3rd-party 2-way integrations (e.g. ERP push, Vercel Blob fully wired) not yet defined. No formal 'set of test transactions' documented.
3 | Integration Capability | C3-SC5 | Integration readiness for applications | Phase 3 | Integration capabilty for third party application | At least one application service ready to integrate with a third party application | Documented integration instructions | Integration instructions, assessor confirmation | Strong | Anthropic SDK fully wired (`@anthropic-ai/sdk` direct provider). Vercel Blob optional wiring present (`@vercel/blob` installed; falls back to local disk when no token). NextAuth supports OAuth providers (just need to enable Google/MS). | Integration instructions document for a hypothetical 3rd-party app not yet written. Assessor confirmation not pursued.
4 | Operational Readiness | C4-SC1 | Delivery governance | Phase 1 | Platform delivery governance documented | Completion of agreed governance artefacts | 100% of agreed governance artefacts completed | Governance playbook, RACI, operating model summary | Partial | CLAUDE.md (PUB project architectural invariants, kept as a navigation layer). Git history is full and meaningful. Long-form chat transcript captures decisions. Memory file `feedback_faithful_port.md` codifies the do-not-simplify rule. | No RACI matrix. No formal governance playbook. No operating model summary.
4 | Operational Readiness | C4-SC2 | Release management | Phase 1 | Release process documented and adopted | Completion of formal release management process | Approved release process in place | Release procedure, approval record, document register | Partial | De-facto release process: push to main → GitHub Actions builds + rsyncs + pm2 reload → live in ~3 min. Workflow file `.github/workflows/deploy.yml` is the procedure-as-code. README in `.github/workflows/`. | No human-readable release procedure document. No approval record per release. No formal document register.
4 | Operational Readiness | C4-SC3 | CI/CD enablement | Phase 2 | Automated deployment pipeline operational | Percentage of agreed environments supported by CI/CD pipeline | 100% of agreed environments supported | CI/CD workflow evidence, pipeline screenshots, deployment logs | Strong | GitHub Actions workflow `deploy.yml` triggers on push to main (paths: web/**). Builds on GH runner, rsyncs to Azure VM, applies new Drizzle migrations idempotently, reloads pm2, smoke-tests public IP. ~3 min end-to-end. Last successful run #26712395245. | Test environment not yet covered by CI/CD (Dev/Prod-like only). Rollback not automated.
4 | Operational Readiness | C4-SC4 | Change and prioritisation control | Phase 1 | Backlog and change control process active | Completion and adoption of prioritisation and change control framework | Approved and in active use | Backlog process document, change log, governance minutes | Partial | BACKLOG.md (this file). Git commit history is the change log. Chat transcript captures prioritisation decisions in real time. | No formal backlog process document. No governance minutes. GitHub Issues / Projects not configured.
4 | Operational Readiness | C4-SC5 | Operational usability and support | Phase 3 | Platform and core modules usable with support ownership defined | Completion of user readiness and support model | Named support ownership active and agreed core modules usable by IOX personnel | Support model, user walkthroughs, acceptance record | Partial | All core modules render + work end-to-end (CostX, BOQs, ProcureX, Projects, Benchmarking, Configuration, Rate Analysis). Sign-in works. Demo data populated. Tag `app=IOX-OS` on all Azure resources. | No documented support model. No user walkthroughs / training material. No formal user acceptance record from IOX personnel.
5 | Platform Launch / First Live Service | C5-SC1 | Production monitoring | Phase 3 | Monitoring and alerting active | Percentage of agreed production monitoring controls enabled | 100% of agreed monitoring controls active | Monitoring dashboard, alert configuration, operations checklist | Weak | pm2 status + pm2 logs (per-process), nginx access/error logs, Postgres logs locally. Activity log table tracks user actions across modules. | No external monitoring (Azure Monitor / Datadog / Sentry). No alerting on crashes / 5xx spikes / queue backups / disk-full. No operations checklist.
5 | Platform Launch / First Live Service | C5-SC2 | Performance validation | Phase 3 | Load and performance tests available | Agreed performance measures available | 100% of agreed performance metrics generated | Load test report, performance test output, assessor review | Not Started | Nothing. | No load testing (k6 / Artillery / JMeter). No baseline RPS / latency / error rate captured. No assessor review.
5 | Platform Launch / First Live Service | C5-SC3 | Production deployment | Phase 3 | First live service deployed | Count of live services/modules successfully deployed to production | Minimum 1 live service/module deployed | Production deployment record, release evidence, go-live approval | Strong | IOX live at http://20.203.125.83 serving 5+ modules: CostX (masterplan list/editor/summary), BOQs (run dashboard), ProcureX (project + tender wizard), Projects, Benchmarking, Configuration, Rate Analysis. All HTTP 200. CI/CD redeploys on every push. | Formal production deployment record (release notes per deploy). No go-live approval signed.
5 | Platform Launch / First Live Service | C5-SC4 | Production quality assurance | Phase 3 | Critical live defects resolved | Number of unresolved critical production defects at sign-off | 0 critical production defects outstanding | Defect log, remediation record, production readiness report | Partial | Defects found in chat have been fixed live: BOQ loader getCell(0) crash, AUTH_TRUST_HOST missing, HeroUI Pro postinstall, NextAuth cookie stale, FoT extraction with empty docs/. Each fix committed. | No formal defect log (severity / status / age tracking). No production readiness report.
5 | Platform Launch / First Live Service | C5-SC5 | Live operational readiness | Phase 3 | Live service stable and usable in practice | Completion of agreed live readiness checks and user validation | Production environment stable for at least a week and agreed live module usable by Omnium personnel | Uptime report, user validation record, go-live sign-off | Weak | App live since today (May 31 2026), no observed crashes since the cookie/heroui fixes. pm2 restart counter at 0. | Not yet stable for 1 week (just deployed). No uptime report. No user validation record from Omnium. No go-live sign-off.

## Summary
IOX KPI Backlog summary
Generated | 2026-05-31T12:29
Status | Count
Strong / Done | 4
Partial | 14
Weak | 3
Not Started | 3
Total | 24
Component | % LoE
Foundation & Security | 10%
Data & Architecture | 45%
Integration Capability | 25%
Operational Readiness | 10%
Platform Launch / First Live Service | 10%