## Fly-Bill 13
BILL NO. 13
REVISED STRUCTURES STRENGTHENING WORKS - GMP

## Bill 13 Revised Strength.
Item | Description | Quantity | Unit | Rate | Amount
|  |  |  | AED | AED
ALTERATIONS
REVISED STRUCTURE STRENGTHENING WORKS
Design Obligation - Vertical & Horizontal Strengthening
A | All design requirements mentioned on the drawings or project specification’s and or authority requirements should be part of the Sub-contractor scope. | 1 | Sum | 0 | Included
B | Full design and detailing and construction of strengthening of Vertical element columns / walls is the Sub-contractor responsibility | 1 | Sum | 0 | Included
C | Full design and detailing and construction of strengthening of Horizontal elements beams and slab, concrete and steel sections is the Sub-contractor responsibility | 1 | Sum | 0 | Included
D | The Sub-contractor shall submit the the full package for strenthening Works to the Authorities and obtain their approval. The submission to Authorities must be fully reviewed and stamped by a 3rd party consultant approved by Trakhees (must use Qualiconsult) ahead of issue to the ERC and onward submission to Authorities for approval. | 1 | Sum | 0 | Included
|  | To Collection |  | AED | 0
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
Strengthening works; including supports, fixings, accessories and all ancillary works as necessary
A | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ01; 150mm thick; 2 sided; to basement 2 | 1.281 | m³ | 12790 | 16383.99
B | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ01; 150mm thick; 3 sided; to basement 2 | 5.9704 | m³ | 12790 | 76361.0962
C | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ01; 150mm thick; 4 sided; to basement 2 | 25.5285 | m³ | 12790 | 326509.515
D | Jacket existing column; size 1250 x 1950 x 3050mm high; CJ01; 150mm thick; 4 sided; to basement 2 | 3.477 | m³ | 12790 | 44470.83
E | Jacket existing column; size 1250 x 2000 x 3050mm high; CJ01; 150mm thick; 3 sided; to basement 2 | 2.3332 | m³ | 12790 | 29842.2675
F | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ02; 150mm thick; 3 sided; to basement 2 | 5.9704 | m³ | 12790 | 76361.0962
G | Jacket existing column; size 1250 x 2000 x 3050mm high; CJ02; 150mm thick; 4 sided; to basement 2 | 7.0455 | m³ | 12790 | 90111.945
H | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ03; 300mm thick; 2 sided; to basement 2 | 5.673 | m³ | 12790 | 72557.67
|  | To Collection |  | AED | 732598.41
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ03; 300mm thick; 3 sided; to basement 2 | 40.7632 | m³ | 12790 | 521361.9675
B | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ03; 300mm thick; 4 sided; to basement 2 | 94.794 | m³ | 12790 | 1212415.26
C | Jacket existing column; size 1250 x 1500 x 3050mm high; CJ03; 300mm thick; 3 sided; to basement 2 | 9.9735 | m³ | 12790 | 127561.065
D | Jacket existing column; size 1250 x 2000 x 3050mm high; CJ03; 300mm thick; 3 sided; to basement 2 | 11.8035 | m³ | 12790 | 150966.765
E | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ04; 200mm thick; 3 sided; to basement 2 | 33.306 | m³ | 12790 | 425983.74
F | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ04; 200mm thick; 4 sided; to basement 2 | 165.066 | m³ | 12790 | 2111194.14
G | Jacket existing column; size 1250 x 2000 x 3050mm high; CJ04; 200mm thick; 4 sided; to basement 2 | 4.941 | m³ | 12790 | 63195.39
H | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ05; 250mm thick; 4 sided; to basement 2 | 5.3375 | m³ | 12790 | 68266.625
J | Jacket existing column; size 1250 x 2000 x 3050mm high; CJ05; 250mm thick; 4 sided; to basement 2 | 12.9625 | m³ | 12790 | 165790.375
K | Jacket existing column; size 500 x 1250 x 3050mm high; CJ06; 150mm thick; 4 sided; to basement 2 | 2.1502 | m³ | 12790 | 27501.6975
|  | To Collection |  | AED | 4874237.025
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 600 x 600 x 3050mm high; CJ06; 150mm thick; 4 sided; to basement 2 | 1.647 | m³ | 12790 | 21065.13
B | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ06; 150mm thick; 3 sided; to basement 2 | 13.9309 | m³ | 12790 | 178175.8912
C | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ06; 150mm thick; 4 sided; to basement 2 | 14.1825 | m³ | 12790 | 181394.175
D | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ07; 150mm thick; 3 sided; to basement 2 | 1.9901 | m³ | 12790 | 25453.6987
E | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ08; 200mm thick; 3 sided; to basement 2 | 5.551 | m³ | 12790 | 70997.29
F | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ08; 200mm thick; 4 sided; to basement 2 | 24.156 | m³ | 12790 | 308955.24
G | Jacket existing column; size 1250 x 1585 x 3050mm high; CJ08; 200mm thick; 4 sided; to basement 2 | 4.4347 | m³ | 12790 | 56719.813
H | Jacket existing column; size 1250 x 2000 x 3050mm high; CJ08; 200mm thick; 4 sided; to basement 2 | 9.882 | m³ | 12790 | 126390.78
J | Jacket existing wall; 200mm thick; 1 sided; to basement 2 | 98.2 | m³ | 12790 | 1255978
K | Jacket existing wall; 200mm thick; 2 sided; to basement 2 | 13.2 | m³ | 12790 | 168828
L | RC wall buttress structure; size 700 x 1300 x 2750mm high; to basement 2 | 5.005 | m³ | 12790 | 64013.95
|  | To Collection |  | AED | 2457971.968
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | RC wall buttress structure; size 700 x 1500 x 2750mm high; to basement 2 | 2.8875 | m³ | 12790 | 36931.125
B | Indicative props spaced at 500mm maximum on centers; 3050mm high; to basement 2 | 327 | Nr. | 118.8942 | 38878.3956
C | Jacket existing column; size 1250 x 1250 x 3550mm high; CJ01; 150mm thick; 3 sided; to basement 1 | 2.3164 | m³ | 12790 | 29626.4362
D | Jacket existing column; size 1250 x 1250 x 3550mm high; CJ01; 150mm thick; 4 sided; to basement 1 | 3.3015 | m³ | 12790 | 42226.185
E | Jacket existing column; size 1250 x 1500 x 3550mm high; CJ01; 150mm thick; 4 sided; to basement 1 | 3.3015 | m³ | 12790 | 42226.185
F | Jacket existing column; size 1250 x 1250 x 3550mm high; CJ03; 300mm thick; 2 sided; to basement 1 | 2.8365 | m³ | 12790 | 36278.835
G | Jacket existing column; size 1250 x 1250 x 3550mm high; CJ04; 200mm thick; 4 sided; to basement 1 | 4.686 | m³ | 12790 | 59933.94
H | Jacket existing column; size 1250 x 1250 x 3550mm high; CJ07; 150mm thick; 3 sided; to basement 1 | 2.3164 | m³ | 12790 | 29626.4362
J | Jacket existing column; size 1250 x 1250 x 3550mm high; CJ08; 200mm thick; 3 sided; to basement 1 | 3.2305 | m³ | 12790 | 41318.095
K | Jacket existing column; size 1250 x 1585 x 3550mm high; CJ08; 200mm thick; 4 sided; to basement 1 | 5.1617 | m³ | 12790 | 66018.143
L | Jacket existing wall; 200mm thick; 1 sided; to basement 1 | 108.4 | m³ | 12790 | 1386436
|  | To Collection |  | AED | 1809499.7761
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing wall; 200mm thick; 2 sided; to basement 1 | 11.6 | m³ | 12790 | 148364
B | RC wall buttress structure; size 700 x 1300 x 3250mm high; to basement 1 | 5.915 | m³ | 12790 | 75652.85
C | RC wall buttress structure; size 700 x 1500 x 3250mm high; to basement 1 | 3.4125 | m³ | 12790 | 43645.875
D | Indicative props spaced at 500mm maximum on centers; 3250mm high; to basement 1 | 323 | Nr. | 118.8942 | 38402.8188
E | Jacket existing column; size 600 x 600 x 3400mm high; CJ01; 150mm thick; 4 sided; to ground floor | 9.18 | m³ | 12790 | 117412.2
F | Jacket existing column; size 1250 x 1250 x 3400mm high; CJ01; 150mm thick; 4 sided; to ground floor | 6.324 | m³ | 12790 | 80883.96
G | Jacket existing column; size 1250 x 1250 x 3700mm high; CJ01; 150mm thick; 4 sided; to ground floor | 3.441 | m³ | 12790 | 44010.39
H | Jacket existing column; size 1250 x 1500 x 3700mm high; CJ01; 150mm thick; 4 sided; to ground floor | 3.7185 | m³ | 12790 | 47559.615
J | Jacket existing column; size 1250 x 2000 x 3700mm high; CJ01; 150mm thick; 4 sided; to ground floor | 4.2735 | m³ | 12790 | 54658.065
K | Jacket existing column; size 600 x 600 x 3400mm high; CJ02; 150mm thick; 4 sided; to ground floor | 1.836 | m³ | 12790 | 23482.44
L | Jacket existing column; size 1250 x 1250 x 3700mm high; CJ02; 150mm thick; 3 sided; to ground floor | 2.4143 | m³ | 12790 | 30878.2575
|  | To Collection |  | AED | 704950.4713
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1250 x 1250 x 3400mm high; CJ04; 200mm thick; 4 sided; to ground floor | 8.976 | m³ | 12790 | 114803.04
B | Jacket existing column; size 1250 x 1250 x 3700mm high; CJ07; 150mm thick; 3 sided; to ground floor | 2.4143 | m³ | 12790 | 30878.2575
C | Jacket existing column; size 1250 x 1585 x 3700mm high; CJ08; 200mm thick; 4 sided; to ground floor | 5.3798 | m³ | 12790 | 68807.642
D | Jacket existing wall; 200mm thick; 1 sided; to ground floor | 59.6 | m³ | 12790 | 762284
E | Jacket existing wall; 200mm thick; 2 sided; to ground floor | 10.8 | m³ | 12790 | 138132
F | RC wall buttress structure; size 700 x 1300 x 3700mm high; to ground floor | 6.734 | m³ | 12790 | 86127.86
G | RC wall buttress structure; size 700 x 1500 x 3700mm high; to ground floor | 3.885 | m³ | 12790 | 49689.15
H | Indicative props spaced at 500mm maximum on centers; 3700mm high; to ground floor | 83 | Nr. | 118.8942 | 9868.2166
J | Jacket existing column; size 600 x 600 x 3750mm high; CJ01; 150mm thick; 4 sided; to ground floor mezzanine | 12.15 | m³ | 12790 | 155398.5
K | Jacket existing column; size 1250 x 1250 x 3850mm high; CJ01; 150mm thick; 4 sided; to ground floor mezzanine | 3.5805 | m³ | 12790 | 45794.595
L | Jacket existing column; size 1250 x 1500 x 3850mm high; CJ01; 150mm thick; 4 sided; to ground floor mezzanine | 3.8692 | m³ | 12790 | 49487.7075
M | Jacket existing column; size 1250 x 1250 x 3850mm high; CJ02; 150mm thick; 4 sided; to ground floor mezzanine | 3.5805 | m³ | 12790 | 45794.595
|  | To Collection |  | AED | 1557065.5636
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1250 x 1250 x 3750mm high; CJ04; 200mm thick; 4 sided; to ground floor mezzanine | 4.95 | m³ | 12790 | 63310.5
B | Jacket existing column; size 1250 x 1250 x 3850mm high; CJ07; 150mm thick; 3 sided; to ground floor mezzanine | 2.5121 | m³ | 12790 | 32130.0787
C | Jacket existing column; size 1250 x 1585 x 3850mm high; CJ08; 200mm thick; 4 sided; to ground floor mezzanine | 5.5979 | m³ | 12790 | 71597.141
D | Jacket existing wall; 200mm thick; 1 sided; to ground floor mezzanine | 71.6 | m³ | 12790 | 915764
E | Jacket existing wall; 200mm thick; 2 sided; to ground floor mezzanine | 12.4 | m³ | 12790 | 158596
F | RC wall buttress structure; size 700 x 1300 x 4300mm high; to ground floor mezzanine | 7.826 | m³ | 12790 | 100094.54
G | RC wall buttress structure; size 700 x 1500 x 4300mm high; to ground floor mezzanine | 4.515 | m³ | 12790 | 57746.85
H | Indicative props spaced at 500mm maximum on centers; 3550mm high; to ground floor mezzanine | 85 | Nr. | 118.8942 | 10106.005
J | Jacket existing column; size 600 x 600 x 3200mm high; CJ01; 150mm thick; 3 sided; to first floor | 1.152 | m³ | 12790 | 14734.08
K | Jacket existing column; size 600 x 600 x 3200mm high; CJ01; 150mm thick; 4 sided; to first floor | 3.456 | m³ | 12790 | 44202.24
L | Jacket existing column; size 600 x 600 x 3500mm high; CJ01; 150mm thick; 4 sided; to first floor | 1.89 | m³ | 12790 | 24173.1
|  | To Collection |  | AED | 1492454.5347
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 900 x 900 x 3200mm high; CJ01; 150mm thick; 4 sided; to first floor | 16.128 | m³ | 12790 | 206277.12
B | Jacket existing column; size 1250 x 1250 x 3500mm high; CJ01; 150mm thick; 4 sided; to first floor | 3.255 | m³ | 12790 | 41631.45
C | Jacket existing column; size 1250 x 1500 x 3500mm high; CJ01; 150mm thick; 4 sided; to first floor | 3.5175 | m³ | 12790 | 44988.825
D | Jacket existing column; size 600 x 600 x 3200mm high; CJ02; 150mm thick; 4 sided; to first floor | 5.184 | m³ | 12790 | 66303.36
E | Jacket existing column; size 900 x 900 x 3200mm high; CJ02; 150mm thick; 4 sided; to first floor | 2.304 | m³ | 12790 | 29468.16
F | Jacket existing column; size 600 x 600 x 3200mm high; CJ03; 300mm thick; 2 sided; to first floor | 3.456 | m³ | 12790 | 44202.24
G | Jacket existing column; size 1250 x 1250 x 3200mm high; CJ04; 200mm thick; 4 sided; to first floor | 4.224 | m³ | 12790 | 54024.96
H | Jacket existing column; size 600 x 600 x 3200mm high; CJ06; 150mm thick; 4 sided; to first floor | 1.728 | m³ | 12790 | 22101.12
J | Jacket existing column; size 1250 x 1250 x 3500mm high; CJ07; 150mm thick; 3 sided; to first floor | 2.2837 | m³ | 12790 | 29209.1625
K | Jacket existing column; size 1250 x 1585 x 3500mm high; CJ08; 200mm thick; 4 sided; to first floor | 5.089 | m³ | 12790 | 65088.31
L | Jacket existing wall; 200mm thick; 1 sided; to first floor | 47.2 | m³ | 12790 | 603688
|  | To Collection |  | AED | 1206982.7075
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing wall; 200mm thick; 2 sided; to first floor | 10.4 | m³ | 12790 | 133016
B | RC thickening below existing beam size 1250 x 900mm; BJ01; size 1250 x 400mm; to first floor | 39 | m³ | 12790 | 498810
C | RC thickening below existing beam size 1250 x 900mm; BJ02; size 1250 x 700mm; to first floor | 15 | m³ | 12790 | 191850
| RC thickening below existing beam size 1250 x 1300mm; BJ03; size 1250 x 700mm; to first floor | 4 | m³ | 12790 | 51160
| RC thickening below existing beam size 1250 x 1300mm; BJ04; size 1250 x 400mm; to first floor | 7 | m³ | 12790 | 89530
D | RC thickening below existing beam size 1250 x 900mm; BJ06; size 1250 x 600mm; to first floor | 6 | m³ | 12790 | 76740
| RC wall buttress structure; size 700 x 1300 x 3500mm high; to first floor | 6.37 | m³ | 12790 | 81472.3
E | RC wall buttress structure; size 700 x 1500 x 3500mm high; to first floor | 3.675 | m³ | 12790 | 47003.25
F | Indicative props spaced at 500mm maximum on centers; 3500mm high; to first floor | 77 | Nr. | 118.89 | 9154.53
G | Jacket existing column; size 600 x 600 x 3050mm high; CJ01; 150mm thick; 4 sided; to first floor mezzanine | 3.294 | m³ | 12790 | 42130.26
H | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ01; 150mm thick; 4 sided; to first floor mezzanine | 2.8365 | m³ | 12790 | 36278.835
J | Jacket existing column; size 1250 x 1500 x 3050mm high; CJ01; 150mm thick; 4 sided; to first floor mezzanine | 3.0652 | m³ | 12790 | 39204.5475
|  | To Collection |  | AED | 1296349.7225
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1250 x 1250 x 2950mm high; CJ04; 200mm thick; 4 sided; to first floor mezzanine | 3.894 | m³ | 12790 | 49804.26
B | Jacket existing column; size 1250 x 1250 x 3050mm high; CJ07; 150mm thick; 3 sided; to first floor mezzanine | 1.9901 | m³ | 12790 | 25453.6987
C | Jacket existing column; size 1250 x 1585 x 3050mm high; CJ08; 200mm thick; 4 sided; to first floor mezzanine | 4.4347 | m³ | 12790 | 56719.813
D | Jacket existing wall; 200mm thick; 1 sided; to first floor mezzanine | 43.4 | m³ | 12790 | 555086
E | Jacket existing wall; 200mm thick; 2 sided; to first floor mezzanine | 9.6 | m³ | 12790 | 122784
F | RC wall buttress structure; size 700 x 1300 x 3500mm high; to first floor mezzanine | 6.37 | m³ | 12790 | 81472.3
G | RC wall buttress structure; size 700 x 1500 x 3500mm high; to first floor mezzanine | 3.675 | m³ | 12790 | 47003.25
H | Indicative props spaced at 500mm maximum on centers; 2750mm high; to first floor mezzanine | 72 | Nr. | 118.8942 | 8560.3807
J | Jacket existing column; size 600 x 600 x 3200mm high; CJ01; 150mm thick; 3 sided; to second floor | 1.152 | m³ | 12790 | 14734.08
K | Jacket existing column; size 600 x 600 x 3200mm high; CJ01; 150mm thick; 4 sided; to second floor | 3.456 | m³ | 12790 | 44202.24
L | Jacket existing column; size 1250 x 1500 x 3500mm high; CJ01; 150mm thick; 4 sided; to second floor | 3.5175 | m³ | 12790 | 44988.825
|  | To Collection |  | AED | 1050808.8474
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 600 x 600 x 3200mm high; CJ02; 150mm thick; 4 sided; to second floor | 3.456 | m³ | 12790 | 44202.24
B | Jacket existing column; size 1100 x 1100 x 3500mm high; CJ02; 150mm thick; 4 sided; to second floor | 2.94 | m³ | 12790 | 37602.6
C | Jacket existing column; size 600 x 600 x 3200mm high; CJ03; 300mm thick; 2 sided; to second floor | 1.728 | m³ | 12790 | 22101.12
D | Jacket existing column; size 600 x 600 x 3200mm high; CJ04; 200mm thick; 4 sided; to second floor | 2.56 | m³ | 12790 | 32742.4
E | Jacket existing column; size 1100 x 1100 x 3500mm high; CJ07; 150mm thick; 2 sided; to second floor | 1.3125 | m³ | 12790 | 16786.875
F | Jacket existing wall; 200mm thick; 1 sided; to second floor | 22.8 | m³ | 12790 | 291612
G | RC thickening below existing beam size 1250 x 900mm; BJ01; size 1250 x 400mm; to second floor | 46 | m³ | 12790 | 588340
H | RC thickening below existing beam size 1250 x 900mm; BJ02; size 1250 x 700mm; to second floor | 2 | m³ | 12790 | 25580
J | RC thickening below existing beam size 1250 x 1300mm; BJ03; size 1250 x 700mm; to second floor | 13 | m³ | 12790 | 166270
K | RC thickening below existing beam size 1250 x 900mm; BJ05; size 1250 x 800mm; to second floor | 16 | m³ | 12790 | 204640
L | RC wall buttress structure; size 700 x 1300 x 3500mm high; to second floor | 6.37 | m³ | 12790 | 81472.3
|  | To Collection |  | AED | 1511349.535
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | RC wall buttress structure; size 700 x 1500 x 3500mm high; to second floor | 3.675 | m³ | 12790 | 47003.25
B | Indicative props spaced at 500mm maximum on centers; 3500mm high; to second floor | 74 | Nr. | 118.8942 | 8798.169
C | Jacket existing column; size 600 x 600 x 3050mm high; CJ01; 150mm thick; 3 sided; to second floor mezzanine | 1.098 | m³ | 12790 | 14043.42
D | Jacket existing column; size 600 x 600 x 3050mm high; CJ01; 150mm thick; 4 sided; to second floor mezzanine | 8.235 | m³ | 12790 | 105325.65
E | Jacket existing column; size 1250 x 1500 x 3050mm high; CJ01; 150mm thick; 4 sided; to second floor mezzanine | 3.0652 | m³ | 12790 | 39204.5475
F | Jacket existing column; size 1100 x 1100 x 3050mm high; CJ02; 150mm thick; 2 sided; to second floor mezzanine | 1.1437 | m³ | 12790 | 14628.5625
G | Jacket existing column; size 600 x 600 x 3050mm high; CJ03; 300mm thick; 2 sided; to second floor mezzanine | 1.647 | m³ | 12790 | 21065.13
H | Jacket existing wall; 200mm thick; 1 sided; to second floor mezzanine | 15.4 | m³ | 12790 | 196966
J | RC wall buttress structure; size 700 x 1300 x 2750mm high; to second floor mezzanine | 5.005 | m³ | 12790 | 64013.95
K | RC wall buttress structure; size 700 x 1500 x 2750mm high; to second floor mezzanine | 2.8875 | m³ | 12790 | 36931.125
L | Indicative props spaced at 500mm maximum on centers; 2700mm high; to second floor mezzanine | 67 | Nr. | 118.8942 | 7965.9098
M | Jacket existing column; size 1100 x 1100 x 3000mm high; CJ01; 150mm thick; 3 sided; to third floor | 1.755 | m³ | 12790 | 22446.45
|  | To Collection |  | AED | 578392.1638
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1100 x 1100 x 3000mm high; CJ01; 150mm thick; 4 sided; to third floor | 5.04 | m³ | 12790 | 64461.6
B | Jacket existing column; size 1250 x 1500 x 3000mm high; CJ01; 150mm thick; 4 sided; to third floor | 3.015 | m³ | 12790 | 38561.85
C | Jacket existing column; size 1100 x 1100 x 3000mm high; CJ02; 150mm thick; 4 sided; to third floor | 5.04 | m³ | 12790 | 64461.6
D | Jacket existing column; size 1100 x 1100 x 3000mm high; CJ09; 150mm thick; 4 sided; to third floor | 2.52 | m³ | 12790 | 32230.8
E | Jacket existing wall; 200mm thick; 1 sided; to third floor | 2.4 | m³ | 12790 | 30696
F | Jacket existing wall; 200mm thick; 2 sided; to third floor | 88.4 | m³ | 12790 | 1130636
G | Indicative props spaced at 500mm maximum on centers; 2650mm high; to third floor | 61 | Nr. | 118.8942 | 7252.5447
H | Jacket existing column; size 600 x 600 x 3100mm high; CJ01; 150mm thick; 2 sided; to lower roof | 0.6975 | m³ | 12790 | 8921.025
J | Jacket existing column; size 600 x 600 x 3100mm high; CJ01; 150mm thick; 4 sided; to lower roof | 1.674 | m³ | 12790 | 21410.46
K | Jacket existing column; size 600 x 600 x 3200mm high; CJ01; 150mm thick; 3 sided; to lower roof | 2.304 | m³ | 12790 | 29468.16
L | Jacket existing column; size 600 x 600 x 3200mm high; CJ01; 150mm thick; 4 sided; to lower roof | 8.64 | m³ | 12790 | 110505.6
|  | To Collection |  | AED | 1538605.6397
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1100 x 1100 x 3100mm high; CJ02; 150mm thick; 4 sided; to lower roof | 5.208 | m³ | 12790 | 66610.32
B | Jacket existing column; size 600 x 600 x 3100mm high; CJ04; 200mm thick; 4 sided; to lower roof | 2.48 | m³ | 12790 | 31719.2
C | Jacket existing column; size 600 x 600 x 3200mm high; CJ04; 200mm thick; 2 sided; to lower roof | 2.048 | m³ | 12790 | 26193.92
D | Jacket existing column; size 675 x 850 x 3200mm high; CJ05; 250mm thick; 2 sided; to lower roof | 3.24 | m³ | 12790 | 41439.6
E | Jacket existing column; size 600 x 600 x 3100mm high; CJ06; 150mm thick; 4 sided; to lower roof | 1.674 | m³ | 12790 | 21410.46
F | Jacket existing wall; 200mm thick; 1 sided; to lower roof | 46.6 | m³ | 12790 | 596014
G | Jacket existing column; size 500 x 500 x 6000mm high; CJ01; 150mm thick; 4 sided; to upper roof | 11.52 | m³ | 12790 | 147340.8
H | Jacket existing column; size 600 x 600 x 5900mm high; CJ01; 150mm thick; 4 sided; to upper roof | 9.558 | m³ | 12790 | 122246.82
J | Jacket existing column; size 600 x 600 x 5950mm high; CJ01; 150mm thick; 4 sided; to upper roof | 3.213 | m³ | 12790 | 41094.27
K | Jacket existing column; size 600 x 600 x 6300mm high; CJ01; 150mm thick; 3 sided; to upper roof | 4.536 | m³ | 12790 | 58015.44
L | Jacket existing column; size 600 x 600 x 6300mm high; CJ01; 150mm thick; 4 sided; to upper roof | 10.206 | m³ | 12790 | 130534.74
|  | To Collection |  | AED | 1282619.57
REVISED STRUCTURE STRENGTHENING WORKS (Cont´d)
A | Jacket existing column; size 1100 x 1100 x 5950mm high; CJ01; 150mm thick; 3 sided; to upper roof | 6.9615 | m³ | 12790 | 89037.585
B | Jacket existing column; size 600 x 600 x 5950mm high; CJ02; 150mm thick; 4 sided; to upper roof | 6.426 | m³ | 12790 | 82188.54
C | Jacket existing column; size 600 x 600 x 6000mm high; CJ02; 150mm thick; 4 sided; to upper roof | 12.96 | m³ | 12790 | 165758.4
D | Jacket existing column; size 1100 x 1100 x 5900mm high; CJ02; 150mm thick; 4 sided; to upper roof | 4.956 | m³ | 12790 | 63387.24
E | Jacket existing column; size 600 x 600 x 6300mm high; CJ04; 200mm thick; 2 sided; to upper roof | 4.032 | m³ | 12790 | 51569.28
F | Jacket existing column; size 600 x 600 x 5950mm high; CJ05; 250mm thick; 4 sided; to upper roof | 13.09 | m³ | 12790 | 167421.1
G | Jacket existing column; size 600 x 600 x 5900mm high; CJ06; 150mm thick; 4 sided; to upper roof | 3.186 | m³ | 12790 | 40748.94
H | Jacket existing wall; 200mm thick; 1 sided; to upper roof | 9.8 | m³ | 12790 | 125342
RC thickening works/ Other than BJ Types
J | RC thickening works at Ground floor at G-01,G-03 to G-06 | 196.7021 | m³ | 12790 | 2515819.859
K | RC Beams at Zone A (S-43206 & S-43204) at first and second fllor | 182.1603 | m³ | 12790 | 2329829.5975
Sundries
L | Additional rebar; dowel connection to existing to new structure | 91.76 | t |  | Included
M | Post fix hilti | 56,067 | Nr. |  | Included
|  | To Collection |  | AED | 5631102.5415
COLLECTION
| Page 13/1/1 |  |  |  | 0
| Page 13/1/2 |  |  |  | 732598.41
| Page 13/1/3 |  |  |  | 4874237.025
| Page 13/1/4 |  |  |  | 2457971.968
| Page 13/1/5 |  |  |  | 1809499.7761
| Page 13/1/6 |  |  |  | 704950.4713
| Page 13/1/7 |  |  |  | 1557065.5636
| Page 13/1/8 |  |  |  | 1492454.5347
| Page 13/1/9 |  |  |  | 1206982.7075
| Page 13/1/10 |  |  |  | 1296349.7225
| Page 13/1/11 |  |  |  | 1050808.8474
| Page 13/1/12 |  |  |  | 1511349.535
| Page 13/1/13 |  |  |  | 578392.1638
| Page 13/1/14 |  |  |  | 1538605.6397
| Page 13/1/15 |  |  |  | 1282619.57
| Page 13/1/16 |  |  |  | 5631102.5415
|  | Carried To Summary |  | AED | 27724988.4762

## Bill 13 Add'l
Item | Description | Quantity | Unit | Rate | Amount
|  |  |  | AED | AED
Post Submission Meeting dated 29th August 2023
Additional Stregthening Works: Edge preparation deemed required but not detailed on drawings
A | Termination & Edge preparation by means of drilling, fixing anchor rebars and grouting them with micro concreting etc., in line with the enclosed markup drawings | 163.3839 | m³ | 12790 | 2089680.081
B | Manual chipping for concrete using manual jackhammers and removal of concrete | 163.3839 | m³ | 2391.356 | 390709.0774
C | Additional Beams to be added as part of horizontal strengthening due to connection with new structure. Scope shall include for: - Surface preparation for location of adding the new beams - Drilling and epoxy anchoring for connections - Installation of Dowel Bars & steel rebars - Shuttering and casting of beams using micro concrete The mark up drawings attached cover all horizontal beams included in the strengthening scope | 57.9975 | m³ | 12790 | 741788.025
|  | Carried To Summary |  | AED | 3222177.1834

## Bill 13 Finishes
Item | Description | Quantity | Unit | Rate | Amount
|  |  |  | AED | AED
ASSOCIATED FINISHES
Finishes to Additional Jacketed Columns
Cement plaster; including surface preparation and all ancillary works as necessary
A | Wall plaster; 15mm thick; to receive paint (Rate as per Bill Reference 3/J/2) | 8489 | m² | 48.0531 | 407922.4501
Paint
B | Paint Finishes to Jacketed Columns (Rate as per Bill Reference 4/J/6 Item B) | 8489 | m² | 42.9699 | 364771.532
Finishes to Additional Jacketed Walls
Cement plaster; including surface preparation and all ancillary works as necessary
C | Wall plaster; 15mm thick; to receive paint (Rate as per Bill Reference 3/J/2) | 6423 | m² | 48.0531 | 308644.8224
Paint
D | Paint Finishes to Jacketed Columns (Rate as per Bill Reference 4/J/6 Item B) | 6423 | m² | 42.9699 | 275995.7062
Finishes to Additional RC Beam Thickening / Jacketing
Cement plaster; including surface preparation and all ancillary works as necessary
E | Wall plaster; 15mm thick; to receive paint (Rate as per Bill Reference 3/J/2) | 2105 | m² | 48.0531 | 101151.6972
Paint
F | Paint Finishes to Jacketed Columns (Rate as per Bill Reference 4/J/6 Item B) | 2105 | m² | 42.9699 | 90451.6521
Adjustments
G | Less Finishes associated w/ Strenghtening Works priced previously |  | sum |  | -169237.97
|  | Carried To Summary |  | AED | 1379699.8901

## Add Scaff SS-Vertical
Dutco Construction Company LLC
T061/22 - Al Khail Mall Redevelopment Works
STRUCTURE STRENGTHENING WORKS - VERTICAL AND HORIZONTAL
Item | Description | Unit | Scaffold Qty | Rate | Rate | Duration | Amount
|  |  |  | for Installation / Unit | for hire of materials/Day | of Hire (Days) | AED
BILL NO. 2- DEMOLITIONS AND ALTERATIONS
ALTERATIONS
STRUCTURE STRENGTHENING WORKS
RC Walls and Columns
1. Demolition Plan Drawing Nr. S-12200 series
2. Demolition Section and Details Drawing Nr. S-30200 series
Strengthening works; including supports, fixings, accessories and all ancillary works as necessary Additional rebar; dowel connection to existing to new structure and Post fix hilti
Basement 2
Refer PTC 30 /Authority approved drawings-series 12100
Section and Details Drawing Nr. S-61001
A | Jacket existing column; size 1250 x 1250 x 3050mm high; to basement 2 -refer S-43316
A.01 | CJ01-150mm thick (12 Nr) | m³ | 390.156 | 45 | 0.45 | 14 | 20015.0028
A.02 | CJ02-150mm thick (3 Nr) | m³ | 97.539 | 45 | 0.45 | 14 | 5003.7507
A.03 | CJ03-300mm thick (27 Nr) | m³ | 942.084 | 45 | 0.45 | 14 | 48328.9092
A.04 | CJ04-200mm thick (53 Nr) | m³ | 1765.218 | 45 | 0.45 | 14 | 90555.6834
A.05 | CJ05-250mm thick (1 Nr) | m³ | 34.099 | 45 | 0.45 | 14 | 1749.2787
A.06 | CJ06-150mm thick (13 Nr) | m³ | 422.669 | 45 | 0.45 | 14 | 21682.9197
A.07 | CJ07-150mm thick (1 Nr) | m³ | 32.513 | 45 | 0.45 | 14 | 1667.9169
A.08 | CJ08-200mm thick (6 Nr) | m³ | 199.836 | 45 | 0.45 | 14 | 10251.5868
0
B | Jacket existing column; size 1250 x 2000 x 3050mm high; to basement 2 -refer S-43316 | [5 empty] | 0
B.01 | CJ01-150mm thick (1 Nr) | m³ | 38.4605 | 45 | 0.45 | 14 | 1973.0236
B.02 | CJ02-150mm thick (2 Nr) | m³ | 76.921 | 45 | 0.45 | 14 | 3946.0473
B.03 | CJ03-300mm thick (2 Nr) | m³ | 81.679 | 45 | 0.45 | 14 | 4190.1327
B.04 | CJ04-200mm thick (1 Nr) | m³ | 39.2535 | 45 | 0.45 | 14 | 2013.7045
B.05 | CJ05-250mm thick (2 Nr) | m³ | 80.093 | 45 | 0.45 | 14 | 4108.7709
B.06 | CJ08-200mm thick (2 Nr) | m³ | 78.507 | 45 | 0.45 | 14 | 4027.4091
B.07 | CJ11-250mm thick (1 Nr) | m³ | 40.0465 | 45 | 0.45 | 14 | 2054.3854
0
C | Jacket existing column; size 1250 x 1500 x 3050mm high; to basement 2 -refer S-43316 | [5 empty] | 0
C.01 | CJ01-150mm thick (1 Nr) | m³ | 34.4955 | 45 | 0.45 | 14 | 1769.6191
C.02 | CJ02-150mm thick (2 Nr) | m³ | 68.991 | 45 | 0.45 | 14 | 3539.2383
C.03 | CJ03-300mm thick (2 Nr) | m³ | 73.749 | 45 | 0.45 | 14 | 3783.3237
|  |  | To Collection | AED |  |  | 230660.703
A | Jacket existing column; size 500 x 1250 x 3050mm high; to basement 2 -refer S-43316
A.01 | CJ06-150mm thick (1 Nr) | m³ | 26.5655 | 45 | 0.45 | 14 | 1362.8101
0
B | Jacket existing column; size 600 x 600 x 3050mm high; to basement 2 -refer S-43316 | [5 empty] | 0
B.01 | CJ06-150mm thick (1 Nr) | m³ | 22.204 | 45 | 0.45 | 14 | 1139.0652
0
C | RC wall buttress structure; size 700 x 1500 x 2750mm high; to basement 2 -refer S-43316 | [5 empty] | 0
C.01 | PUL-W01 (3 Nr) | m³ | 75.075 | 45 | 0.45 | 14 | 3851.3475
0
D | Wall Jacketing- 3.050m high | [5 empty] | 0
D.01 | 200mm thk wall jacketing (105 M) | m³ | 416.325 | 45 | 0.45 | 14 | 21357.4725
D.02 | CJ10-300mm thick (59 M) | m³ | 233.935 | 45 | 0.45 | 14 | 12000.8655
D.03 | CJ01-150mm thick (8 M) | m³ | 31.72 | 45 | 0.45 | 14 | 1627.236
D.04 | CJ08-200mm thick (6 M) | m³ | 23.79 | 45 | 0.45 | 14 | 1220.427
|  |  | To Collection | AED |  |  | 42559.2238
STRUCTURE STRENGTHENING WORKS (Cont'd)
Basement 1
A | Jacket existing column; size 1250 x 1250 x 3250mm high; to basement 1
A.01 | CJ01-150mm thick (2 Nr) | m³ | 69.29 | 45 | 0.45 | 14 | 3554.577
A.03 | CJ03-300mm thick (1 Nr) | m³ | 37.18 | 45 | 0.45 | 14 | 1907.334
A.04 | CJ04-200mm thick (1 Nr) | m³ | 35.49 | 45 | 0.45 | 14 | 1820.637
A.07 | CJ07-150mm thick (1 Nr) | m³ | 34.645 | 45 | 0.45 | 14 | 1777.2885
A.08 | CJ08-200mm thick (2 Nr) | m³ | 70.98 | 45 | 0.45 | 14 | 3641.274
0
B | Jacket existing column; size 1250 x 2000 x 3250mm high; to basement 1 -refer S-43316 | [5 empty] | 0
B.01 | CJ01-150mm thick (1 Nr) | m³ | 40.9825 | 45 | 0.45 | 14 | 2102.4023
0
C | RC wall buttress structure; size 700 x 1500 x 3270mm high; to basement 2 -refer S-43316 | [5 empty] | 0
C.01 | PUL-W01 (3 Nr) | m³ | 89.271 | 45 | 0.45 | 14 | 4579.6023
0
D | Wall Jacketing- 3.250m high |  | 0 |  |  |  | 0
D.01 | 200mm thk wall jacketing (105 M) | m³ | 443.625 | 45 | 0.45 | 14 | 22757.9625
D.02 | CJ10-300mm thick (62 M) | m³ | 261.95 | 45 | 0.45 | 14 | 13438.035
|  |  | To Collection | AED |  |  | 55579.1126
STRUCTURE STRENGTHENING WORKS (Cont'd)
Ground floor
A | Jacket existing column; size 1250 x 1250 x 3700mm high; to ground floor
A.01 | CJ01-150mm thick (3 Nr) | m³ | 118.326 | 45 | 0.45 | 14 | 6070.1238
A.02 | CJ02-150mm thick (1 Nr) | m³ | 39.442 | 45 | 0.45 | 14 | 2023.3746
A.03 | CJ04-200mm thick (2 Nr) | m³ | 80.808 | 45 | 0.45 | 14 | 4145.4504
A.04 | CJ07-150mm thick (1 Nr) | m³ | 39.442 | 45 | 0.45 | 14 | 2023.3746
A.05 | CJ08-200mm thick (1 Nr) | m³ | 40.404 | 45 | 0.45 | 14 | 2072.7252
0
B | Jacket existing column; size 1250 x 1500 x 3700mm high; to ground floor | [5 empty] | 0
B.01 | CJ01-150mm thick (2 Nr) | m³ | 93.314 | 45 | 0.45 | 14 | 4787.0082
0
C | Jacket existing column; size 600 x 600 x 3700mm high; to ground floor | [5 empty] | 0
C.01 | CJ01-150mm thick (5 Nr) | m³ | 134.68 | 45 | 0.45 | 14 | 6909.084
C.02 | CJ02-150mm thick (1 Nr) | m³ | 26.936 | 45 | 0.45 | 14 | 1381.8168
0
D | Wall Jacketing- 3.70m high | [5 empty] | 0
D.01 | 200mm thk wall jacketing (105 M) | m³ | 505.05 | 45 | 0.45 | 14 | 25909.065
0
E | RC wall buttress structure; size 700 x 1500 x 21550mm high; to Ground to third floor-refer S-43316 | [5 empty] | 0
E.01 | PUL-W01 (3 Nr) | m³ | 588.315 | 45 | 0.45 | 14 | 30180.5595
0
0
0
0
| Ground floor mezzanine | [5 empty] | 0
0
G | Wall Jacketing- 3.55m high | [5 empty] | 0
G.01 | 200mm thk wall jacketing (105 M) | m³ | 484.575 | 45 | 0.45 | 14 | 24858.6975
0
H | Jacket existing column; size 1250 x 1250 x 3550mm high; to ground floor | [5 empty] | 0
H.01 | CJ01-150mm thick (1 Nr) | m³ | 37.843 | 45 | 0.45 | 14 | 1941.3459
H.02 | CJ02-150mm thick (1 Nr) | m³ | 37.843 | 45 | 0.45 | 14 | 1941.3459
H.03 | CJ04-200mm thick (1 Nr) | m³ | 38.766 | 45 | 0.45 | 14 | 1988.6958
H.04 | CJ07-150mm thick (1 Nr) | m³ | 37.843 | 45 | 0.45 | 14 | 1941.3459
H.05 | CJ08-200mm thick (1 Nr) | m³ | 38.766 | 45 | 0.45 | 14 | 1988.6958
0
J | Jacket existing column; size 1500 x 1250 x 3550mm high; to ground floor | [5 empty] | 0
J.01 | CJ01-150mm thick (1 Nr) | m³ | 40.1505 | 45 | 0.45 | 14 | 2059.7206
0
K | Jacket existing column; size 600 x 600 x 3550mm high; to ground floor | [5 empty] | 0
K.01 | CJ01-150mm thick (6 Nr) | m³ | 155.064 | 45 | 0.45 | 14 | 7954.7832
|  |  | To Collection | AED |  |  | 130177.2128
STRUCTURE STRENGTHENING WORKS (Cont'd)
First floor
A | Jacket existing column; size 1250 x 1250 x 3500mm high; to first floor
A.01 | CJ01-150mm thick (1 Nr) | m³ | 37.31 | 45 | 0.45 | 14 | 1914.003
A.02 | CJ04-200mm thick (1 Nr) | m³ | 38.22 | 45 | 0.45 | 14 | 1960.686
A.03 | CJ07-150mm thick (1 Nr) | m³ | 37.31 | 45 | 0.45 | 14 | 1914.003
A.04 | CJ08-200mm thick (1 Nr) | m³ | 38.22 | 45 | 0.45 | 14 | 1960.686
B | Jacket existing column; size 1500 x 1250 x 3500mm high; to first floor
B.01 | CJ01-150mm thick (1 Nr) | m³ | 39.585 | 45 | 0.45 | 14 | 2030.7105
C | Jacket existing column; size 600 x 600 x 3500mm high; to first floor
C.01 | CJ01-150mm thick (4 Nr) | m³ | 101.92 | 45 | 0.45 | 14 | 5228.496
C.02 | CJ02-150mm thick (3 Nr) | m³ | 76.44 | 45 | 0.45 | 14 | 3921.372
C.03 | CJ03-300mm thick (1 Nr) | m³ | 28.21 | 45 | 0.45 | 14 | 1447.173
C.04 | CJ06-150mm thick (1 Nr) | m³ | 25.48 | 45 | 0.45 | 14 | 1307.124
D | Jacket existing column; size 900 x 900 x 3500mm high; to first floor
D.01 | CJ01-150mm thick (7 Nr) | m³ | 216.58 | 45 | 0.45 | 14 | 11110.554
D.02 | CJ02-150mm thick (1 Nr) | m³ | 30.94 | 45 | 0.45 | 14 | 1587.222
E | Wall Jacketing- 3.50m high |  | 0
E.01 | 200mm thk wall jacketing (76 M) | m³ | 345.8 | 45 | 0.45 | 14 | 17739.54
E.02 | CJ08-200mm thick (9 M) | m³ | 40.95 | 45 | 0.45 | 14 | 2100.735
First floor mezzanine
G | Jacket existing column; size 1250 x 1250 x 2750mm high; to first floor mezzanine
G.01 | CJ01-150mm thick (1 Nr) | m³ | 29.315 | 45 | 0.45 | 14 | 1503.8595
G.02 | CJ04-200mm thick (1 Nr) | m³ | 30.03 | 45 | 0.45 | 14 | 1540.539
G.03 | CJ07-150mm thick (1 Nr) | m³ | 29.315 | 45 | 0.45 | 14 | 1503.8595
G.04 | CJ08-200mm thick (1 Nr) | m³ | 30.03 | 45 | 0.45 | 14 | 1540.539
H | Jacket existing column; size 1500 x 1250 x 2750mm high; to first floor mezzanine
H.01 | CJ01-150mm thick (1 Nr) | m³ | 31.1025 | 45 | 0.45 | 14 | 1595.5582
J | Jacket existing column; size 600 x 600 x 2750mm high; to first floor mezzanine
J.01 | CJ01-150mm thick (2 Nr) | m³ | 40.04 | 45 | 0.45 | 14 | 2054.052
K | Wall Jacketing- 3.70m high |  | 0
K.01 | 200mm thk wall jacketing (48 M) | m³ | 230.88 | 45 | 0.45 | 14 | 11844.144
K.02 | CJ08-200mm thick (8 M) | m³ | 38.48 | 45 | 0.45 | 14 | 1974.024
|  |  | To Collection | AED |  |  | 77778.8798
STRUCTURE STRENGTHENING WORKS (Cont'd)
Second floor
A | Jacket existing column; size 1250 x 1250 x 3500mm high; to second floor
A.01 | CJ02-150mm thick (1 Nr) | m³ | 37.31 | 45 | 0.45 | 14 | 1914.003
A.02 | CJ07-150mm thick (1 Nr) | m³ | 37.31 | 45 | 0.45 | 14 | 1914.003
A.03 | CJ09-150mm thick (4 Nr) | m³ | 149.24 | 45 | 0.45 | 14 | 7656.012
B | Jacket existing column; size 1500 x 1250 x 3500mm high; to second floor
B.01 | CJ01-150mm thick (1 Nr) | m³ | 39.585 | 45 | 0.45 | 14 | 2030.7105
C | Jacket existing column; size 600 x 600 x 3500mm high; to second floor
C.01 | CJ01-150mm thick (3 Nr) | m³ | 76.44 | 45 | 0.45 | 14 | 3921.372
C.02 | CJ02-150mm thick (2 Nr) | m³ | 50.96 | 45 | 0.45 | 14 | 2614.248
C.03 | CJ03-300mm thick (1 Nr) | m³ | 28.21 | 45 | 0.45 | 14 | 1447.173
C.04 | CJ04-200mm thick (1 Nr) | m³ | 26.39 | 45 | 0.45 | 14 | 1353.807
D | Wall Jacketing- 3.50m high
D.01 | 200mm thk wall jacketing (18 M) | m³ | 81.9 | 45 | 0.45 | 14 | 4201.47
D.02 | CJ01-150mm thick (5 M) | m³ | 22.75 | 45 | 0.45 | 14 | 1167.075
D.03 | CJ08-200mm thick (12 M) | m³ | 54.6 | 45 | 0.45 | 14 | 2800.98
Second floor mezzanine
F | Jacket existing column; size 1250 x 1250 x 2700mm high; to second floor mezzanine
F.01 | CJ02-150mm thick (2 Nr) | m³ | 57.564 | 45 | 0.45 | 14 | 2953.0332
F.02 | CJ09-150mm thick (4 Nr) | m³ | 115.128 | 45 | 0.45 | 14 | 5906.0664
G | Jacket existing column; size 1250 x 1500 x 2700mm high; to second floor mezzanine
G.01 | CJ01-150mm thick (1 Nr) | m³ | 30.537 | 45 | 0.45 | 14 | 1566.5481
H | Jacket existing column; size 600 x 600 x 2700mm high; to second floor mezzanine
H.01 | CJ01-150mm thick (6 Nr) | m³ | 117.936 | 45 | 0.45 | 14 | 6050.1168
H.02 | CJ02-150mm thick (1 Nr) | m³ | 19.656 | 45 | 0.45 | 14 | 1008.3528
J | Wall Jacketing- 2.70m high
J.01 | 200mm thk wall jacketing (5 M) | m³ | 17.55 | 45 | 0.45 | 14 | 900.315
J.02 | CJ01-150mm thick (5 M) | m³ | 17.55 | 45 | 0.45 | 14 | 900.315
J.03 | CJ08-200mm thick (15 M) | m³ | 52.65 | 45 | 0.45 | 14 | 2700.945
|  |  | To Collection | AED |  |  | 53006.5458
STRUCTURE STRENGTHENING WORKS (Cont'd)
Third floor
A | Jacket existing column; size 1250 x 1250 x 2650mm high; to third floor
A.01 | CJ01-150mm thick (3 Nr) | m³ | 84.747 | 45 | 0.45 | 14 | 4347.5211
A.02 | CJ02-150mm thick (2 Nr) | m³ | 56.498 | 45 | 0.45 | 14 | 2898.3474
A.03 | CJ09-150mm thick (1 Nr) | m³ | 28.249 | 45 | 0.45 | 14 | 1449.1737
B | Jacket existing column; size 1500 x 1250 x 2650mm high; to third floor
B.01 | CJ01-150mm thick (1 Nr) | m³ | 29.9715 | 45 | 0.45 | 14 | 1537.5379
C | Wall Jacketing- 2.70m high
C.01 | 200mm thk wall jacketing (78 M) | m³ | 273.78 | 45 | 0.45 | 14 | 14044.914
C.02 | CJ01-150mm thick (4 M) | m³ | 14.04 | 45 | 0.45 | 14 | 720.252
Lower Roof
E | Jacket existing column; size 1250 x 1250 x 3000mm high; to lower roof floor
E.01 | CJ01-150mm thick (2 Nr) | m³ | 63.96 | 45 | 0.45 | 14 | 3281.148
F | Jacket existing column; size 600 x 600 x 3000mm high; to lower roof floor
F.01 | CJ01-150mm thick (9 Nr) | m³ | 196.56 | 45 | 0.45 | 14 | 10083.528
F.02 | CJ04-200mm thick (3 Nr) | m³ | 67.86 | 45 | 0.45 | 14 | 3481.218
F.03 | CJ05-250mm thick (2 Nr) | m³ | 46.8 | 45 | 0.45 | 14 | 2400.84
F.04 | CJ06-150mm thick (1 Nr) | m³ | 21.84 | 45 | 0.45 | 14 | 1120.392
G | Wall Jacketing- 3.70m high
G.01 | 200mm thk wall jacketing (60 M) | m³ | 288.6 | 45 | 0.45 | 14 | 14805.18
G.02 | CJ01-150mm thick (15 M) | m³ | 72.15 | 45 | 0.45 | 14 | 3701.295
H | Jacket existing column; size 1250 x 1250 x 4650mm high; to upper roof floor
H.01 | CJ01-150mm thick (4 Nr) | m³ | 198.276 | 45 | 0.45 | 14 | 10171.5588
H.02 | CJ02-150mm thick (1 Nr) | m³ | 49.569 | 45 | 0.45 | 14 | 2542.8897
H.03 | CJ04-200mm thick (2 Nr) | m³ | 101.556 | 45 | 0.45 | 14 | 5209.8228
J | Jacket existing column; size 600 x 600 x 4650mm high; to upper roof floor
J.01 | CJ01-150mm thick (11 Nr) | m³ | 372.372 | 45 | 0.45 | 14 | 19102.6836
J.02 | CJ02-150mm thick (6 Nr) | m³ | 203.112 | 45 | 0.45 | 14 | 10419.6456
J.03 | CJ05-250mm thick (2 Nr) | m³ | 72.54 | 45 | 0.45 | 14 | 3721.302
J.04 | CJ06-150mm thick (1 Nr) | m³ | 33.852 | 45 | 0.45 | 14 | 1736.6076
|  |  | To Collection | AED |  |  | 116775.8573
COLLECTION
| Page V/1 - Basement 2 Part 1 | [5 empty] | 230660.703
| Page V/2 - Basement 2 Part 2 | [5 empty] | 42559.2238
| Page V/3 - Basement 1 | [5 empty] | 55579.1126
| Page V/4 - Ground Floor + GF Mezzanine | [5 empty] | 130177.2128
| Page V/5 - First Floor + 1F Mezzanine | [5 empty] | 77778.8798
| Page V/6 - Second Floor + 2F Mezzanine | [5 empty] | 53006.5458
| Page V/7 - Third Floor + Lower Roof (Parking Levels) | [5 empty] | 116775.8573
|  |  | Carried To Summary | AED |  |  | 706537.535

## Add Scaff SS- Horiz
Dutco Construction Company LLC
T061/22 - Al Khail Mall Redevelopment Works
STRUCTURE STRENGTHENING WORKS - VERTICAL AND HORIZONTAL
Item | Description | Unit | Scaffold Qty | Rate | Rate | Duration | Amount
|  |  |  | for Installation / Unit | for hire of materials/Day | of Hire (Days) | AED
BILL NO. 2- DEMOLITIONS AND ALTERATIONS
ALTERATIONS
STRUCTURE STRENGTHENING WORKS
RC Beam Thickening/Jacketing
RC thickening work various thickeness -Reinforced concrete; compressive strength 60 MPa with cement type CEM I+GGBS + including steel fixing and dowel bars (BJ+Beam thickening)
Ground floor
A | RC Beams - various sizes at G-01 (Ref. S-43126) | m³ | 199.8 | 45 | 0.45 | 14 | 10249.74
B | RC Beams - various sizes at G-03 (Ref. S-43126) | m³ | 364.08 | 45 | 0.45 | 14 | 18677.304
C | RC Beams - various sizes at G-04 (Ref. S-43127) | m³ | 390.72 | 45 | 0.45 | 14 | 20043.936
D | RC Beams - various sizes at G-05 (Ref. S-43128) | m³ | 164.28 | 45 | 0.45 | 14 | 8427.564
E | RC Beams - various sizes at G-06 (Ref. S-43129) | m³ | 590.52 | 45 | 0.45 | 14 | 30293.676
First & Second Floor
F | RC Beams at Zone A (S-43206 & S-43204) | m³ | 743.4 | 45 | 0.45 | 14 | 38136.42
Beam Jacketing First and Second Floor - Zone 1&3
Drawing Reference: S -12141, S -12143, S -12151, S -12153
G | BJ-01 | m³ | 871.08 | 45 | 0.45 | 14 | 44686.404
H | BJ-03 | m³ | 109.2 | 45 | 0.45 | 14 | 5601.96
J | BJ-04 | m³ | 63 | 45 | 0.45 | 14 | 3231.9
K | BJ-05 | m³ | 67.2 | 45 | 0.45 | 14 | 3447.36
L | BJ-06 | m³ | 33.6 | 45 | 0.45 | 14 | 1723.68
|  |  | Carried To Summary |  |  |  | 184519.944

## Add Scaffolding-Summary
Dutco Construction Company LLC
T061/22 - Al Khail Mall Redevelopment Works
STRUCTURE STRENGTHENING WORKS - VERTICAL AND HORIZONTAL SUMMARY
Item | Description | Page Ref. | Amount
AED
SUMMARY
| SCAFFOLDING TO COLUMNS / WALLS (JACKETING) |  | 706537.535
| SCAFFOLDING TO RC BEAM / THICKENING (JACKETING) |  | 184519.944
| ADJUSTMENT TO SCAFFOLDING - AGREED W/ OMNIUM |  | -124748.05
| Carried To Main Summary |  | 766309.4289

## Omit Scaff SS
Dutco Construction Company LLC
T061/22 - Al Khail Mall Redevelopment Works
STRUCTURE STRENGTHENING WORKS - VERTICAL AND HORIZONTAL
Item | Description | Unit | Scaffold Qty | Rate | Rate | Duration | Amount
|  |  |  | for Installation / Unit | for hire of materials/Day | of Hire (Days) | AED
BILL NO. 2- DEMOLITIONS AND ALTERATIONS
ALTERATIONS
STRUCTURE STRENGTHENING WORKS
Jacket existing column & RC Wall Buttress Structures
A | To various sizes at different locations | m2 | 1632.1135 | 45 | 0.45 | 14 | 83727.4226
|  |  | Carried To Summary |  |  |  | 83727.4226 | 83727.42
0.00255

## Bill 13 Scaffolding
Item | Description | Quantity | Unit | Rate | Amount
|  |  |  | AED | AED
ACCESS SCAFFOLDING
Scaffolding to Additional Jacketed Columns
A | Access Scaffolding for add'l Strengthening Works | 1 | item | 766309.4289 | 766309.4289
B | Less Scaffolding associated w/ Strenghtening Works priced previously | -1 | item | 83727.4226 | -83727.4226
The above amounts are based on the below schedule of rates
C | Erection / Dismantling of scaffold | 1 | m³ | 45 | RATE ONLY
D | Rate for hire of scaffold materials | 1 | m³-day | 14 | RATE ONLY
|  | Carried To Summary |  | AED | 682582.0064

## Bill 13-Sum
Item | Description | Page Nr. | Amount AED
SUMMARY
| REVISED STRENGTHENING WORKS | 13/1/1 - 13/1/16 | 27724988.4762
| ADDITIONAL STRENGTHENING WORKS (NOT DETAILED ON DRAWINGS) | 13/2/1 | 3222177.1834
| ASSOCIATED FINISHES | 13/3/1 | 1379699.8901
| ACCESS SCAFFOLDING TO STRENGTHENING WORKS | 13/4/1 | 682582.0064
TOTAL FOR BILL NO. 13 - STRENGHTENING WORKS GMP
| TO MAIN SUMMARY | AED | 33009447.556